## Hoja1
| Task | Team member | Estimated time | Time
2017-03-27 | 0.1 - Scroll | Adri/Victor/Valdi | 3h | 3h
2017-03-27 | 0.1 - Player & PlayerControl | Victor | 1h 30min | 1h
2017-03-27 | 0.1 - Yuan-nang sprites movement animations | Varela | 1h 30min | 2h
2017-03-27 | 0.1 - Music Module | Adri/Valdi | 1h | 20min
2017-03-27 | 0.1 Write Github Readme 0.1 Version and start writing information | Varela | 30min | 1h
2017-03-12 | Rip Sprites | Victor | 6h | 8h
2017-03-12 | Rip Sprites | Valdi | 5h | 8h | Total Time: | Estimated | Real
2017-03-31 | 0.2 - Implement fade to black | Everyone | 3h | 2h | Adrià Grionès | 73h 51min | 78h 47min
2017-03-31 | 0.2 Write Github presentation information and web page | Varela | 30min | 1h | Victor Tirado | 29h 10min | 30h 15min
2017-04-02 | SDL6 - Make lasers work | Adri/Valdi | 3h | 2h | David Varela | 12 h 45min | 19h 50min
2017-04-02 | 0.3 - Implement lasers | Valdi | 30min | 30min | David Valdivia | 30h 40min | 36h 30min
2017-04-02 | 0.3 - Implement 2nd character (Marion) | Adri/Victor | 2h | 1h
2017-04-05 | Create module enemy | Victor/Valdi | 1h | 1h
2017-04-07 | Add enemy (Balloon) | Victor | 30min | 25min
2017-04-07 | Balloon colisions | Adri | 20min | 30min
2017-04-12 | 0.42 - implement castle background | Valdi | 30min | 25min
2017-04-12 | 0.42 - implement enemy modules | Valdi | 30min | 45min
2017-04-13 | Implement explosion particles | Victor | 40min | 1h 10min
2017-04-13 | Organize PNG images | Victor | 30min | 30 min
2017-04-13 | Implement some enemy | Adri | 2h | 2h
2017-04-14 | Enemy collisons | Adri | 1h | 3h
2017-04-14 | Fix bugs | Adri | 30 min | 1h
2017-04-14 | Readjust animation speeds | Valdi | 10min | 10min
2017-04-14 | Implement power up | Valdi | 1h | 1h 30min
2017-04-14 | PowerUp animations | Valdi | 15min | 10min
2017-04-14 | Implement PowerUp collision and Level Up condition | Adri | 1 h | 2h
2017-04-14 | Organize Assets | Valdi | 15min | 15min
2017-04-15 | Module UI: credits, lives, bombs, start | Adri | 2h | 2h
2017-04-15 | Module UI: Player 2 | Adri | 3h | 3h
2017-04-15 | Add all lasers Yuan Nang + audio | Adri | 30 min | 30 min
2017-04-15 | Fix OGG archives | Valdi | 10min | 10mn
2017-04-15 | Fix bugs | Adri | 1h | 1h
2017-04-15 | Lasers with level up condition Yuan Nang | Adri | 30 min | 30 min
2017-04-16 | Bug fixing | Valdi | 30min | 35min
2017-04-16 | Implement 5 character module | Adri | 5h | 5h
2017-04-16 | Spritesheet of all characters in game | Varela | 15min | 1h
2017-04-16 | Disable/Enable Player 2 with coins | Adri | 1h | 1h
2017-04-16 | Character Selection UI | Adri | 2h | 2h
2017-04-16 | Implement Module Audio | Adri | 2h | 2 h
2017-04-16 | Fix bugs | Adri | 1h | 1h
2017-04-17 | Fix bugs, add hitboxes & hitpoints | Valdi | 30min | 30min
2017-04-17 | Make/fix character animations | Valdi | 1 30min | 2h
2017-04-17 | Character Selection Animations | Adri | 1 h 15 min | 1h 15 min
2017-04-17 | Implement UI of Lives for all characters | Adri | 30 min | 30 min
2017-04-17 | Fix particle speeds | Adri | 15 min | 15 min
2017-04-17 | Create a particle of an enemy | Adri | 15 min | 15 min
2017-04-17 | Implement castle turret shot | Adri | 15 min | 30 min
2017-04-17 | Implement characters' voice: Dead, selected and power up | Adri | 30 min | 30 min
2017-04-17 | Fix Module Audio | Adri | 15 min | 45 min
2017-04-17 | Implement decreasing enemy life when shot | Adri | 15 min | 15 min
2017-04-18 | All UI of the 5 Characters (Character Select Done except countdown) | Adri | 5h | 5h
2017-04-14 | Implement enemies | Victor | 4h | 4h
2017-05-15 | Extract sprites | Victor | 2h | 2h
2017-04-19 | Implement bridge animations | Victor | 1h | 1h 45min
2017-04-18 | Implement tetsu animations | Victor | 30 min | 30 min
2017-04-18 | Implement tetsu animations | Varela | 1h | 2h
2017-04-19 | Fix Scroll Castle | Adri | 30 min | 30 min
2017-04-20 | Implement Marion lasers | Valdi | 1h | 1h 30min
2017-04-20 | Implement Ash lasers | Valdi | 1h | 2h
2017-04-20 | Implement soldiers (background animations) | Victor | 1h | 2h
2017-04-20 | Fix 2 Players input | Adri | 2h | 2h
2017-04-20 | Implement enemy shot directed to the player | Adri | 2h | 2h
2017-04-20 | Implement player death | Adri | 2h | 6h
2017-04-21 | Implement enemy drone | Victor | 40 min | 30 min
2017-04-21 | Fix Yuan Nang lasers | Valdi | 3h | 4h
2017-04-21 | Implement Tetsu lasers | Valdi | 1h | 1h 30min
2017-04-21 | Module Fonts + Score for the 2 players | Adri | 4h | 4h
2017-04-21 | Choose 2nd Player in the background screen | Adri | 4h | 4h
2017-04-21 | Implement Game Over screen | Adri | 2h | 2h
2017-04-21 | Implement Tetsu lasers | Valdi | 1h | 1h
2017-04-22 | Implement coin item | Victor | 2h | 1h 30 min
2017-04-22 | Implement immortal animation for the player | Victor | 20min | 25min
2017-04-22 | Fix bugs (Spawn, Death ) | Adri | 3h | 3h
2017-04-22 | Implement God Mode, direct Win / direct Lose | Adri | 3h | 3h
2017-04-22 | Icon Marion in the .exe archive | Adri | 5min | 5min
2017-04-22 | Fix bugs (change control) | Adri | 10min | 10min
2017-04-23 | Fix Tetsu sprite animations | Varela | 1h | 6h
2017-04-23 | Implement Score Screen | Adri | 4h | 4h
2017-04-24 | Final retouches | Valdi | 10min | 10min
2017-04-24 | Fix bugs: debug functionality gates | Adri/Valdi | 30min | 45min
2017-04-24 | Implement the game over timer | Adri/Valdi | 20min | 15min
2017-04-25 | Rip more sprites | Varela | 4h | 3h 35min
2017-04-25 | Add Spritesheets | Varela | 1h | 1h 15 min
2017-04-25 | Implement animation when player shot hits a enemy | Adri/Valdi | 2h | 2h
2017-04-25 | Implement score for 10 puntuations organized with highest ranking order | Adri | 1h | 1h